## Test Scenarios
Test Scenarios
Project Name | Lightnig Proxies
Clint | Lightnig Proxies
Created By | Shivendra Singh
Created Date | 2025-01-04
Approval date
Approved By | Lightnig Proxies
Browser/OS | Chrome, Firefox, Edge/Window10
Test Scenario ID | Test Scenario | Priority | Total Test cases | Fail
TS-01 | Verify Signup Module Page | P1 | 12 | 1
TS-02 | Verify Login Page | P1 | 10 | 0
TS-03 | Verify Dashboard Page | P1 | 36 | 1
TS-04 | Verify Purchase Plan | P1 | 24 | 1
TS-05 | Verify Deposit Balance Module | P2 | 19 | 1
TS-06 | Verify Invoices | P2 | 18 | 0
TS-07 | Verify Proxy Usage Log | P2 | 17 | 0
TS-08 | Verify Refferal | P3 | 18 | 1
TS-09 | Verify FAQs Page | P0 | 12 | 1
TS-10 | Verify Proxy Guide Page | P2 | 27 | 3
TS-11 | Verify Join Discord Server & Telegram Channel | P4 | 11 | 1
TS-12 | Verify Profile Page | P1 | 21 | 3
|  |  | 225 | 13

## SignUP
TEST CASES for "SignUP"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-01 | Functional | Verify Signup Module Page | TC_001 | Browser is opened and user is on the https://app.lightningproxies.net/register | Redirect to SignUp page | 1. Open The Browser. 2. visit to " https://app.lightningproxies.net/register " | NA | link should Redirect to SignUp page | it should redirected to SignUp page | Pass | as expected
|  |  | TC_002 | Browser is opened and user is on the https://app.lightningproxies.net/register | Verify username, email, password fields accept valid inputs | 1. Navigate to Create Account page 2. Enter valid username, email, password 3. Click on Create Account button | Username: Shivendra , Email- shivendramasai2024@gmail.com , Password- Singh@7607 | Account should be created successfully | Account successfully created | Pass | inputs works properly
|  |  | TC_003 | Browser is opened and user is on the https://app.lightningproxies.net/register | Check if appropriate error messages appear for incorrect inputs | 1. Navigate to Create Account page 2. Enter invalid email format 3. Click on Create Account | Email- shivendrasingh6945@gmail.co | Error message should be displayed | Error message should be displayed | Fail | user should able to login by filling incomplete email format
|  |  | TC_004 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure password meets strength requirements | 1. Enter weak password 2. Click on Create Account | Password: 12345 | Weak password message should be displayed | Weak password message should be displayed | Pass | as expected
|  |  | TC_005 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure password and confirm password fields match | 1. Enter mismatched passwords 2. Click on Create Account | Password- Singh@4545 Confirm- Singh@7607 | Error message should be displayed | Error message should be displayed | Pass | as expected
|  |  | TC_006 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure CAPTCHA verification is mandatory | 1. Try creating an account without checking CAPTCHA | None | Error message should be displayed | Error message should be displayed | Pass | as expected
| Usability |  | TC_007 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure elements are aligned properly | 1. Check UI elements on different screen sizes | None | UI should be properly aligned | UI should be properly aligned | Pass | as expected
|  |  | TC_008 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure third-party authentication works | 1. Click on 'Sign up with Google' 2. Authenticate | Google credentials | User should be signed up successfully | User should be signed up successfully | Pass | as expected
| Performance |  | TC_009 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure form submission is quick | 1. Fill the form 2. Submit | Valid user data | Response time- 2s | Response time- 2s | Pass | Submission is quick
| Accessibility |  | TC_010 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure screen readers can read form labels | 1. Use a screen reader tool | None | Screen reader should read labels properly | Screen reader should read labels properly | Pass | as expected
| Cross-Browser |  | TC_011 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure the form works across browsers | 1. Open page on Chrome, Firefox, Edge | None | Page should work consistently | Page should work consistently | Pass | as expected
| Security |  | TC_012 | Browser is opened and user is on the https://app.lightningproxies.net/register | Ensure password is encrypted before transmission | 1. Enter password 2. Inspect network calls | Password- Singh@7607 | Password should not be in plain text | Password should not be in plain text | Pass | works properly

## Login
TEST CASES for "Login"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
| UI Testing | Verify user login | TC_01 | Browser is opened and user is already registered | Ensure that all UI elements are properly displayed | 1. Open The Browser. 2. visit to "https://app.lightningproxies.net/login" | NA | All UI elements should be displayed properly | All UI elements should be displayed properly | Pass | As expected
TS-02 | Functional |  | TC_02 | Browser is opened and user is already registered | Ensure the login functionality works with correct details | 1. Navigate to the login page 2. Enter valid username and password 3. Click 'Login' button | Username- Shivendra Singh Password- Singh@7607 | User should be logged in successfully | User should be logged in successfully | Pass | logged in successfully
|  |  | TC_03 | Browser is opened and user is already registered | Ensure the system rejects incorrect passwords | 1. Enter valid username and incorrect password 2. Click 'Login' button | Username- sdsdsd Password- Ddd@7789 | Error message should appear | Error message should appear | Pass | As expected
|  |  | TC_04 | Browser is opened and user is already registered | System should prevent login for unregistered users | 1. Enter unregistered username and any password 2. Click 'Login' button | Username- Tanvi Password: Tanvi@5544 | Error message should appear | Error message should appear | Pass | As expected
|  |  | TC_05 | Browser is opened and user is already registered | Ensure password recovery link is sent | 1. Click 'Forgot password?' 2. Enter registered email 3. Submit request | Email- shivendramasai2024@gmail.com | Password reset email should be sent | Password reset email should be sent | Pass | Reset Password Works Properly
| Usability |  | TC_06 | Browser is opened and user is already registered | Ensure all UI elements are correctly displayed | 1. Open the login page 2. Verify input fields, buttons, labels, and branding | NA | All elements should be visible and aligned | All elements should be visible and aligned | Pass | Works as expected
| Performance |  | TC_07 | Browser is opened and user is already registered | Ensure login request is processed within acceptable time | 1. Enter credentials 2. Click 'Login' 3. Measure response time | NA | Login should be processed within 2 seconds | Login should be processed within 2 seconds | Pass | Works as expected
| Accessibility |  | TC_08 | Browser is opened and user is already registered | Ensure CAPTCHA prevents bot logins | 1. Attempt login without solving CAPTCHA 2. Solve CAPTCHA and retry login | NA | CAPTCHA should be required before login | CAPTCHA should be required before login, it shows error message | Pass | shows error message when without filling CAPTCHA
| Cross-Browser |  | TC_09 | Browser is opened and user is already registered | Ensure the login page works properly on all browsers | 1. Open the login page in Chrome, Firefox, Edge 2. Verify UI and functionality | NA | Page should work consistently across browsers | Page should work consistently across browsers | Pass | As expected
| Accessibility |  | TC_10 | Browser is opened and user is already registered | Ensure the page is accessible for visually impaired users | 1. Enable screen reader 2. Navigate the page 3. Verify elements are read properly | NA | All elements should be readable by screen readers | All elements should be readable by screen readers | Pass | As expected

## Dashboard
TEST CASES for "Dashboard"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-03 | UI Testing | Verify Dashboard Page | TC_01 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure all UI elements are correctly displayed | 1. Navigate to the dashboard 2. Verify if the balance, active plans, data left, and user profile sections are properly aligned | NA | All UI elements should be correctly aligned and visible | All UI elements should be correctly aligned and visible | Pass | As expected
| Functional Testing |  | TC_02 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure balance is correctly displayed | 1. Navigate to the dashboard 2. Check the "Active Balance" section | NA | Balance should be displayed accurately | Balance should be displayed accurately | Pass | As Expected
|  |  | TC_03 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure the "Add Balance" button is functional | 1. Click on "Add Balance" 2. Verify if the deposit page opens | NA | The deposit page should open | The deposit page should open | Pass | As Expected
|  |  | TC_04 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure the "Purchase Plan" button works correctly | 1. Click on "Purchase Plan" 2. Verify if the purchase page opens | NA | The purchase page should open | The purchase page should open | Pass | visited properly
|  |  | TC_05 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure "Data Left" is correctly displayed | 1. Navigate to the dashboard 2. Check the "Data Left" section | NA | Data left should be displayed accurately | Data left should be displayed accurately | Pass | visited properly
|  |  | TC_06 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure entering a valid gift code adds balance | 1. Enter a valid gift code 2. Click "Get your gift" | Valid gift code | The balance should increase accordingly | The balance should increase accordingly | Pass | As Expected
|  |  | TC_07 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure entering an invalid gift code shows an error | 1. Enter an invalid gift code 2. Click "Get your gift" | Invalid gift code | An error message should be displayed | An error message should be displayed | Pass | As Expected
|  |  | TC_08 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure user details are displayed correctly | 1. Navigate to the profile section 2. Verify the username, user ID, and icons | NA | User details should match account information | User details should match account information | Pass | As Expected
|  |  | TC_09 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure profile icons (email, delete, etc.) are functional | 1. Click each profile icon and verify its functionality | NA | Each icon should perform the expected action | All icons should perform the expected action | Pass | Works properly
|  |  | TC_10 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure notifications are displayed properly | 1. Click on the notification area 2. Verify if notifications open | NA | Notifications should open properly | Notifications should open properly | Pass | it opens
| Usability Testing |  | TC_11 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure users can easily navigate the dashboard | 1. Click on various sections and verify navigation | NA | Navigation should be intuitive and smooth | Navigation should be intuitive and smooth | Pass | Navigation is smooth
|  |  | TC_12 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure light/dark mode toggle works correctly | 1. Click on the toggle switch 2. Verify the UI changes | NA | The UI should switch between light and dark modes | The UI should switch between light and dark modes | Pass | Dark mode is stable and works properly
| Performance Testing |  | TC_13 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure the dashboard loads quickly | 1. Open the dashboard 2. Measure page load time | NA | The page should load within 2 seconds | The page should load within 2 seconds | Pass | As expected
| Accessibility Testing |  | TC_15 | User is using a screen reader | Ensure the page is readable for visually impaired users | 1. Enable screen reader 2. Navigate through the dashboard | NA | Screen reader should read all important information | Screen reader should read all important information | Pass | As expected
|  |  | TC_16 | User is using only a keyboard | Ensure the page can be navigated via keyboard | 1. Use Tab/Arrow keys to navigate 2. Verify all elements are accessible | NA | The user should be able to navigate without a mouse | The user should be able to navigate without a mouse | Pass | As expected
| Cross-Browser Testing |  | TC_17 | User accesses the dashboard on multiple browsers | Ensure the page works properly on Chrome, Firefox, Edge | 1. Open the dashboard on different browsers 2. Verify UI and functionality | NA | The dashboard should work consistently across browsers | The dashboard should work consistently across browsers | Pass | It works in mainly browsers
| Cross-Device Testing |  | TC_18 | User accesses the dashboard on mobile devices | Ensure the page adapts correctly to mobile screens | 1. Open the dashboard on a mobile device 2. Verify layout and usability | NA | The page should be mobile-friendly | The page should be mobile-friendly | Pass | all pages is moble friendly
| Security Testing |  | TC_19 | User is logged in | Ensure session expires after inactivity | 1. Log in to the dashboard 2. Stay inactive for a set time 3. Try performing an action | 2 Hours | The user should be logged out after session timeout | The user should be not logged out after session timeout | Fail | Session always logged in
|  |  | TC_20 | User logs in and refreshes the page | Ensure session persists after a page refresh | 1. Log in to the dashboard 2. Refresh the page | NA | The user should remain logged in | The user should remain logged in | Pass | Its Working properly
| Functional Testing |  | TC_21 | User is logged in | Ensure the user can log out successfully | 1. Click on the profile dropdown 2. Click on the "Logout" button | NA | User should be logged out and redirected to the login page | User should be logged out and redirected to the login page | Pass | works as expected
|  |  | TC_22 | User has an active plan | Ensure "Data Left" is displayed correctly based on plan usage | 1. Navigate to the dashboard 2. Compare actual data left with usage | Sample usage data | "Data Left" should be calculated correctly | "Data Left" should be calculated correctly | Pass | works as expected
|  |  | TC_23 | User is logged in | Ensure the "Read More" link in the notification panel opens the correct page | 1. Click on the "Read More" link | NA | The relevant details page should open | The relevant details page should open | Pass | As expected
|  |  | TC_24 | User is logged in | Ensure clicking the Telegram button opens the support chat | 1. Click on the Telegram button | NA | Telegram support chat should open | Telegram support chat should opened | Pass | It works
|  |  | TC_25 | User has toggled dark mode | Ensure dark mode settings persist after refresh | 1. Enable dark mode 2. Refresh the page | NA | Dark mode should remain enabled | Dark mode should remain enabled | Pass | As expected
| Usability Testing |  | TC_26 | User is logged in | Ensure all buttons are clickable and responsive | 1. Click each button 2. Verify response time | NA | Buttons should be clickable without delay | Buttons should be clickable without delay | Pass | Works Properly
|  |  | TC_28 | User is logged in | Ensure hover effects work on clickable elements | 1. Hover over buttons and links | NA | Elements should change color or show effects on hover | Elements should change color or show effects on hover | Pass | It works
| Performance Testing |  | TC_29 | User has limited bandwidth | Ensure dashboard loads properly under slow network | 1. Simulate slow network (3G) 2. Load the dashboard | Slow network | Dashboard should remain usable with minimal delay | Dashboard should remain usable with minimal delay | Pass | Dashboard is usable
|  |  | TC_30 | User is logged in on multiple devices | Ensure system handles multiple active logins correctly | 1. Log in from multiple devices 2. Perform actions simultaneously | NA | Dashboard should not crash, and sessions should be valid | Dashboard should not crash, and sessions should be valid | Pass | As expected
|  |  | TC_31 | User has multiple plans and high data usage | Ensure dashboard loads correctly with large data | 1. Load a dashboard with high data usage | Large dataset | Page should load without UI breaking | Page should load without UI breaking | Pass | As expected
| Accessibility Testing |  | TC_35 | User enables high contrast mode | Ensure the dashboard is visible in high contrast settings | 1. Enable high contrast mode 2. Navigate through the dashboard | High contrast mode | Text and UI should remain readable | Text and UI should remain readable | Pass | UI is readable
|  |  | TC_36 | User zooms in/out on browser | Ensure the UI remains functional at different zoom levels | 1. Zoom in (200%) 2. Zoom out (50%) | N/A | UI should remain properly aligned and readable | UI should remain properly aligned and readable | Pass | Zoom works properly

## Purchase Plan
TEST CASES for "Purchase Plan"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-04 | Functional | Verify the Purchase Plan Page | TC_01 | verify User opens the landing page | Ensure the page loads completely without errors | 1. Open the website 2. Observe if the elements load correctly | N/A | The page should load without broken images or missing elements | The page should load without broken images or missing elements | Pass | loads properly
|  |  | TC_02 | User is on the landing page | Ensure all plans appear with the correct name, price, and features | 1. Scroll through the plans 2. Compare with expected data | Plan details from database | Plans should match the expected details | Plans should match the expected details | Pass | As expected
|  |  | TC_03 | User is on the landing page | Ensure clicking on "Purchase Plan" redirects correctly | 1. Click "Purchase Plan" on any plan 2. Check if redirection is correct | N/A | User should be taken to the checkout/payment page | User should be taken to the checkout/payment page | Pass | it works properly
|  |  | TC_04 | User is on the landing page | Ensure that selecting different filters updates the displayed plans correctly | 1. Click on filters (Residential, Mobile, Datacenter) 2. Observe the results | Filter options | Only relevant plans should be displayed | Only relevant plans should be displayed | Pass | As expected
|  |  | TC_05 | User selects a plan | Ensure correct pricing is displayed | 1. Choose different plans 2. Compare displayed price | Plan price list | The correct price should be displayed for each plan | The correct price should be displayed for each plan | Pass | As expected
|  |  | TC_06 | User is on the landing page | Ensure clicking on the link redirects to terms page | 1. Click "Terms & Conditions" 2. Verify redirection | N/A | User should be redirected to the Terms page | Terms and conditions link is not functional | Fail | Need to make it functional
| Usability |  | TC_07 | User accesses site on different devices | Ensure site elements adjust properly on various screen sizes | 1. Open site on mobile, tablet, and desktop 2. Check UI | Mobile, tablet, desktop | The layout should remain user-friendly and not break | The layout should remain user-friendly and not break | Pass | It works on all screen sizes
|  |  | TC_08 | User is on the landing page | Ensure all text is readable and properly formatted | 1. Observe text font size and contrast | Various text elements | Text should be clear and readable | Text should be clear and readable | Pass | As expected
|  |  | TC_09 | User is on the landing page | Ensure hover effects work correctly on clickable buttons | 1. Hover over "Purchase Plan" and other buttons | N/A | Buttons should visually indicate interactivity | Buttons should visually indicate interactivity | Pass | As expected
| Performance |  | TC_10 | User is on the landing page | Ensure the page loads within an acceptable time limit | 1. Load the page 2. Measure load time | N/A | Page should load in under 2 seconds | Page should load in under 2 seconds | Pass | As expected
|  |  | TC_11 | User has a slow internet connection | Ensure the page loads properly under network throttling | 1. Simulate slow network 2. Load the page | Slow network | Page should load with minimal disruption | Page should load with minimal disruption | Pass | As expected
| Security |  | TC_13 | User accesses the site using HTTP | Ensure HTTP requests redirect to HTTPS | 1. Open the page using HTTP 2. Observe URL change | HTTP URL | Site should redirect to HTTPS | Site should redirect to HTTPS | Pass | Redirected to HTTPS
|  |  | TC_14 | User is not logged in | Ensure unauthorized users cannot complete a purchase | 1. Attempt purchase without logging in | N/A | User should be prompted to log in first | User should be prompted to log in first | Pass | As expected
|  |  | TC_15 | User inputs SQL commands in form fields | Ensure SQL injection attacks are prevented | 1. Enter SQL commands in search/filter fields | OR 1=1 -- | System should block malicious input | System should block malicious input | Pass | As expected
| Accessibility |  | TC_16 | User navigates using a keyboard | Ensure users can navigate using only the keyboard | 1. Use Tab key to navigate 2. Verify focus on elements | N/A | All interactive elements should be accessible via keyboard | All interactive elements should be accessible via keyboard | Pass | As expected
|  |  | TC_17 | User relies on screen reader | Ensure content is read correctly by assistive technology | 1. Use a screen reader (NVDA, JAWS) 2. Navigate the site | Screen reader software | All text should be read clearly and correctly | All text should be read clearly and correctly | Pass | All content is readable
|  |  | TC_18 | User with visual impairments accesses site | Ensure text and background contrast is sufficient | 1. Use accessibility tools to check contrast | N/A | Contrast should meet WCAG 2.1 AA standards | Contrast should meet WCAG 2.1 AA standards | Pass | Contrast is stable
| Cross-Browser |  | TC_19 | User accesses site on Chrome | Ensure all features work on Chrome | 1. Open the site in Chrome 2. Test key functions | Chrome browser | The site should work as expected | The site should work as expected | Pass | As expected
|  |  | TC_21 | User accesses site on Edge | Ensure all features work on Edge | 1. Open the site in Edge 2. Test key functions | Edge browser | The site should work as expected | The site should work as expected | Pass | As expected
|  |  | TC_22 | User accesses site on Firefox | Ensure all features work on Firefox | 1. Open the site in Firefox 2. Test key functions | Firefox browser | The site should work as expected | The site should work as expected | Pass | As expected
| Compatibility |  | TC_23 | User accesses the site on mobile | Ensure the site works on various mobile devices | 1. Open the site on Android and iOS devices 2. Test navigation | Android, iOS | Site should be fully functional on mobile | Site should be fully functional on mobile | Pass | As expected
|  |  | TC_24 | User accesses the site on a tablet | Ensure the site works on tablets | 1. Open the site on iPad and Android tablets 2. Test navigation | iPad, Android tablet | Site should be fully functional on tablets | Site should be fully functional on tablets | Pass | As expected

## Deposit Balance
TEST CASES for "Deposit Balance"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-05 | Functional Testing | Verify Deposit Balance Module | TC_01 | User is logged in | Verify that the Deposit Balance page loads properly | 1. Open the Deposit Balance page 2. Observe page layout and components | N/A | The page should load without errors | The page should load without errors | Pass | Loads Properly
|  |  | TC_02 | User is on the Deposit Balance page | Verify that the top-up amount input field accepts numeric values | 1. Enter valid numeric value 2. Click outside the input field | 100, 500, 999.99 | The value should be accepted without errors | The value should be accepted without errors | Pass | all values allowed
|  |  | TC_03 | User is on the Deposit Balance page | Verify that the top-up amount input does not accept non-numeric characters | 1. Enter alphabets or special characters 2. Check validation message | abc, @#!$ | System should prevent input and display a validation message | System should not prevent input and not displayed a validation message | Fail | it allows all special character
|  |  | TC_04 | User has entered a valid top-up amount | Verify that the "Add Balance using Cryptocurrency" button is functional | 1. Enter amount 2. Click "Add Balance using Cryptocurrency" | 555 | User should be redirected to the cryptocurrency payment page | User should be redirected to the cryptocurrency payment page | Pass | it says first update the billing data
|  |  | TC_05 | User has entered a valid top-up amount | Verify that the "Add Balance using Stripe" button is functional | 1. Enter amount 2. Click "Add Balance using Stripe" | 555 | User should be redirected to Stripe payment page | User should be redirected to Stripe payment page | Pass | it says first update the billing data
|  |  | TC_06 | User has not updated billing details | Ensure that the system does not allow a transaction without billing info | 1. Try to proceed without billing info 2. Observe the error message | NA | System should display "Billing Information Required" message | System should display "Billing Information Required" message | Pass | As expected
|  |  | TC_07 | User has incomplete billing info | Verify that clicking "Go to profile page" redirects correctly | 1. Click "Go to profile page" 2. Verify page redirection | NA | User should be redirected to the profile settings page | User should be redirected to the profile settings page | Pass | As expected
|  |  | TC_08 | User is on the Deposit Balance page | Ensure the list of supported cryptocurrencies is displayed | 1. Check the list of cryptocurrencies 2. Compare with expected values | BTC, ETH, USDT, LTC, etc. | List should display all supported cryptocurrencies correctly | List should display all supported cryptocurrencies correctly | Pass | As expected
| Usability |  | TC_09 | User is on the Deposit Balance page | Ensure all buttons are easily clickable and functional | 1. Check button color, hover effect, and clickability | NA | Buttons should have clear visibility and functionality | Buttons should have clear visibility and functionality | Pass | As expected
|  |  | TC_10 | User is on the Deposit Balance page | Ensure text is readable, aligned properly, and elements are well-spaced | 1. Observe text size, contrast, and alignment | NA | Text should be clear and easily readable | Text should be clear and easily readable | Pass | As expected
| Performance |  | TC_11 | User is on the Deposit Balance page | Ensure page loads within a few seconds | 1. Open the page 2. Measure load time | NA | Page should load in under 3 seconds | Page should load in under 3 seconds | Pass | As expected
|  |  | TC_12 | User is on payment gateway | Ensure smooth and fast transaction processing | 1. Complete a payment 2. Measure processing time | Payment details | Payment should be processed within a reasonable time | Payment should be processed within a reasonable time | Pass | As expected
|  |  | TC_13 | User has a slow internet connection | Verify site behavior under slow network conditions | 1. Simulate slow network 2. Try making a deposit | Slow network | Page should load with minimal disruption | Page should load with minimal disruption | Pass | As expected
| Security |  | TC_14 | User inputs SQL commands in the amount field | Ensure SQL injection attacks are prevented | 1. Enter SQL commands in input field 2. Try proceeding | OR 1=1 -- | System should block malicious input | System should block malicious input | Pass | As expected
| Accessibility |  | TC_15 | User navigates using a keyboard | Ensure the page is fully navigable using the keyboard | 1. Use Tab key to navigate 2. Check focus on elements | NA | All interactive elements should be accessible via keyboard | All interactive elements should be accessible via keyboard | Pass | As expected
|  |  | TC_16 | User has visual impairments | Ensure text and background contrast is sufficient | 1. Use accessibility tools to check contrast | NA | Contrast should meet WCAG 2.1 AA standards | Contrast should meet WCAG 2.1 AA standards | Pass | As expected
| Cross-Browser |  | TC_17 | User accesses site on Chrome | Ensure all features work on Chrome | 1. Open the site in Chrome 2. Test key functions | Chrome browser | The site should work as expected | The site should work as expected | Pass | As expected
|  |  | TC_18 | User accesses site on Edge | Ensure all features work on Edge | 1. Open the site in Edge 2. Test key functions | Edge browser | The site should work as expected | The site should work as expected | Pass | As expected
|  |  | TC_19 | User accesses site on Firefox | Ensure all features work on Firefox | 1. Open the site in Firefox 2. Test key functions | Firefox browser | The site should work as expected | The site should work as expected | Pass | As expected

## Invoices
TEST CASES for "Invoices"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-06 | Landing Page Testing | Verify that the Invoices page loads correctly | TC_01 | User is logged in and navigates to the Invoices page | Ensure that all elements load without errors | 1. Open the Invoices page 2. Observe UI elements | NA | Page should load without any errors, displaying invoice details | Page should load without any errors, displaying invoice details | Pass | Loads properly
| Functional Testing | Verify that invoice details are displayed correctly | TC_02 | User has existing invoices | Ensure invoice details such as ID, plan, status, payment status, and amount are displayed correctly | 1. Open the Invoices page 2. Verify displayed invoice details | Invoice data | Details should match database records | Details should match database records | Pass | As expected
|  | Verify the search functionality | TC_03 | User has multiple invoices | Ensure the search field filters invoices correctly | 1. Enter a valid invoice ID 2. Verify the filtered results | First Invoice ID- 67d3120c51e67895f651b158 Second Invoice ID- 67d3115951e67895f6519a7a | The correct invoice should be displayed | The correct invoice should be displayed | Pass | As expected
|  | Verify sorting by payment status | TC_04 | User is on the Invoices page | Ensure sorting functionality works correctly | 1. Click "Unpaid" 2. Click "Paid" 3. Observe sorting order | NA | Invoices should be filtered based on selection | Invoices should be filtered based on selection | Pass | As expected
|  | Verify redirection on clicking "View" action | TC_05 | User is on the Invoices page | Ensure that clicking "View" redirects to invoice details | 1. Click "View" on an invoice 2. Check redirection | Invoice ID | User should be redirected to the invoice details page | User should be redirected to the invoice details page | Pass | Redirected successfully
| Usability Testing | Verify the visibility of invoice details | TC_06 | User is on the Invoices page | Ensure text and contrast are readable | 1. Check text size, contrast, and element spacing | NA | Text should be clear and readable | Text should be clear and readable | Pass | All test is clear and readable
|  | Verify responsiveness of the page | TC_07 | User accesses page on different devices | Ensure page adjusts properly on various screen sizes | 1. Open page on desktop 2. Open page on mobile 3. Observe layout changes | Mobile, tablet, desktop | Page should be fully responsive | Page should be fully responsive | Pass | Works properly
| Performance Testing | Verify page load time | TC_08 | User opens the Invoices page | Ensure page loads within acceptable time | 1. Open the page 2. Measure load time | NA | Page should load in <3 seconds | Page should load in <3 seconds | Pass | Loads Fastly
|  | Verify search response time | TC_09 | User searches for an invoice | Ensure search results appear quickly | 1. Enter a search query 2. Measure time taken | Invoice ID | Results should appear in <2 seconds | Results should appear in <2 seconds | Pass | Loads Fastly
| Security Testing | Verify that invoice details cannot be accessed by unauthorized users | TC_10 | User is not logged in | Ensure unauthorized users cannot access invoice data | 1. Try to open Invoices page without logging in | NA | User should be redirected to login page | User should be redirected to login page | Pass | As expected
|  | Verify SQL Injection protection | TC_11 | User is on the Invoices page | Ensure search field does not allow SQL Injection | 1. Enter malicious SQL query 2. Observe system response | OR 1=1 -- | System should prevent SQL injection | System should prevent SQL injection | Pass | As expected
| Accessibility Testing | Verify keyboard navigation | TC_12 | User navigates with a keyboard | Ensure users can access elements using Tab key | 1. Use Tab to navigate through the page | NA | All interactive elements should be accessible | All interactive elements should be accessible | Pass | As expected
| Cross-Browser Testing | Verify functionality on Chrome | TC_13 | User accesses the page on Chrome | Ensure all elements function correctly | 1. Open page in Chrome 2. Test key functions | Chrome browser | Page should work as expected | Page should work as expected | Pass | Works Properly
|  | Verify functionality on Firefox | TC_14 | User accesses the page on Firefox | Ensure all elements function correctly | 1. Open page in Firefox 2. Test key functions | Firefox browser | Page should work as expected | Page should work as expected | Pass | Works Properly
|  | Verify functionality on Edge | TC_15 | User accesses the page on Edge | Ensure all elements function correctly | 1. Open page in Edge 2. Test key functions | Edge browser | Page should work as expected | Page should work as expected | Pass | Works Properly
| Error Handling Testing | Verify handling of invalid invoice searches | TC_16 | User enters a non-existent invoice ID | Ensure system handles invalid searches gracefully | 1. Enter incorrect invoice ID 2. Observe response | Invalid ID- 87s7580c51e78895f441b275 | System should not show any data | System should not show any data | Pass | As expected

## Proxy uses logs
TEST CASES for "Proxy uses logs"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-07 | Landing Page Testing | Verify Proxy uses logs Module | TC_01 | User is logged in and navigates to the Proxy Usage page | Ensure that all elements load without errors | 1. Open the Proxy Usage page 2. Observe UI elements | N/A | Page should load without any errors, displaying proxy usage details | Page should load without any errors, displaying proxy usage details | Pass | Loads Properly
| Functional |  | TC_02 | User has proxy usage data | Ensure bandwidth logs display correct data | 1. Open the Proxy Usage page 2. Verify displayed bandwidth logs | Proxy usage data | Logs should match actual usage | Logs should match actual usage | Pass | As Expected
|  |  | TC_03 | User is on the Proxy Usage page | Ensure user can select a valid date range | 1. Select a start date 2. Select an end date 3. Observe displayed data | Various date ranges | Data should be filtered based on selection | Data should be filtered based on selection | Pass | As Expected
|  |  | TC_04 | User is on the Proxy Usage page | Ensure filtering works correctly | 1. Select different proxy types 2. Observe displayed data | Residential, Mobile, IPv6, Datacenter | Displayed data should change based on selection | Displayed data should change based on selection | Pass | As Expected
|  |  | TC_05 | User is on the Proxy Usage page | Ensure dropdown allows selecting a plan | 1. Click "Select a plan" 2. Choose a plan 3. Observe displayed data | Different plans | Data should update according to the selected plan | Data should update according to the selected plan | Pass | As Expected
|  |  | TC_06 | User is on the Proxy Usage page | Ensure time range buttons filter data correctly | 1. Click "Last hour" 2. Click "Last 24 hours" 3. Observe data updates | Last hour, Last 24 hours, Last 7 days, Last 30 days | Data should update according to the selected range | Data should update according to the selected range | Pass | As Expected
| Usability |  | TC_07 | User is on the Proxy Usage page | Ensure text is clear and readable | 1. Check text size, contrast, and element spacing | NA | Text should be legible with proper contrast | Text should be legible with proper contrast | pass | As Expected
|  |  | TC_08 | User accesses page on different devices | Ensure page adjusts properly on various screen sizes | 1. Open page on desktop 2. Open page on mobile 3. Observe layout changes | Mobile, tablet, desktop | Page should be fully responsive | Page should be fully responsive | pass | As Expected
| Performance |  | TC_09 | User opens the Proxy Usage page | Ensure page loads within acceptable time | 1. Open the page 2. Measure load time | NA | Page should load in <3 seconds | Page should load in <3 seconds | Pass | As Expected
|  |  | TC_10 | User filters data | Ensure filtering results appear quickly | 1. Apply a filter 2. Measure time taken | Proxy type, date range | Data should update in <2 seconds | Data should update in <2 seconds | Pass | As Expected
| Security |  | TC_11 | User is not logged in | Ensure unauthorized users cannot access proxy usage data | 1. Try to open Proxy Usage page without logging in | NA | User should be redirected to login page | User should be redirected to login page | Pass | As Expected
|  |  | TC_12 | User is on the Proxy Usage page | Ensure search and filters do not allow SQL Injection | 1. Enter malicious SQL query 2. Observe system response | OR 1=1 -- | System should prevent SQL injection | System should prevent SQL injection | Pass | As Expected
| Accessibility |  | TC_13 | User navigates with a keyboard | Ensure users can access elements using Tab key | 1. Use Tab to navigate through the page | NA | All interactive elements should be accessible | All interactive elements should not be accessible | Fail | Need to fix
| Cross-Browser |  | TC_14 | User accesses the page on Chrome | Ensure all elements function correctly | 1. Open page in Chrome 2. Test key functions | Chrome browser | Page should work as expected | Page should work as expected | Pass | As Expected
|  |  | TC_15 | User accesses the page on Firefox | Ensure all elements function correctly | 1. Open page in Firefox 2. Test key functions | Firefox browser | Page should work as expected | Page should work as expected | Pass | As Expected
|  |  | TC_16 | User accesses the page on Edge | Ensure all elements function correctly | 1. Open page in Edge 2. Test key functions | Edge browser | Page should work as expected | Page should work as expected | Pass | As Expected
|  |  | TC_17 | No proxy usage data exists | Ensure system handles missing data gracefully | 1. Open Proxy Usage page 2. Observe displayed message | NA | System should display "No data available" message | System should display "No data available" message | Pass | As Expected

## Refferal
TEST CASES for "Refferal"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-10 | Landing Page Testing | Verify the Referrals page | TC_01 | User is logged in and navigates to the Referrals page | Ensure that all elements load without errors | 1. Open the Referrals page 2. Observe UI elements | NA | Page should load without any errors, displaying referral details | Page should load without any errors, displaying referral details | Pass | As expected
| Functional |  | TC_02 | User is on the Referrals page | Ensure referral link is unique to each user | 1. Navigate to the Referrals page 2. Check the referral link 3. Compare with another user’s referral link | Unique user ID | Each user should have a unique referral link | Each user should have a unique referral link | Pass | As expected
|  |  | TC_03 | User has a referral link | Ensure the link redirects correctly to the registration page | 1. Copy the referral link 2. Open it in a new browser tab 3. Observe the landing page | Referral link- https://app.lightningproxies.net/register?referral=67d191b351e67895f61a6002 | The link should redirect to the correct registration page | The link should redirect to the correct registration page | Pass | successfully redirected to the correct page
|  |  | TC_04 | User has unclaimed earnings | Ensure clicking the button initiates the withdrawal process | 1. Click on "Claim Earnings" 2. Observe the system response | $10 unclaimed earnings | A prompt should appear to confirm earnings claim | A prompt should appear to confirm earnings claim | Pass | As expected
|  |  | TC_05 | User has referred a new user who made a purchase | Ensure earnings update upon referral's purchase | 1. Refer a user 2. Wait for referral to make a purchase 3. Check earnings balance | Purchase amount-based commission | Earnings should increase based on referral purchase | Earnings should increase based on referral purchase | Pass | As expected
|  |  | TC_06 | User has referred others | Ensure the number of active referral users updates properly | 1. Refer a user 2. Have them register and purchase 3. Observe the "Active Referral Users" count | 1 referral user | The active referral user count should increase | The active referral user count should increase | Pass | As expected
| Usability |  | TC_07 | User is on the Referrals page | Ensure readability of text and contrast | 1. Observe text size and contrast 2. Check readability and word responsiveness on different devices | Desktop and Mobile | Text responsiveness should be clear and readable | Text should be clear and readable but it is not responsive | Fail | Need to fix- (earn and discount) use capital letter for starting words
|  |  | TC_08 | User is on the Referrals page | Ensure users can understand how referrals work | 1. Read the referral instructions 2. Check for clarity and ease of understanding | Default referral instructions | Instructions should clearly describe how to earn rewards | Instructions should clearly describe how to earn rewards | Pass | As expected
| Performance |  | TC_09 | User opens the Referrals page | Ensure the page loads within an acceptable time | 1. Open the page 2. Measure load time | NA | Page should load in <3 seconds | Page should load in <3 seconds | Pass | Loads properly
|  |  | TC_10 | User filters referral data | Ensure filtering results appear quickly | 1. Apply a filter 2. Measure time taken | Search user ID | Data should update in <2 seconds | Data should update in <2 seconds | Pass | As expected
| Accessibility |  | TC_11 | User navigates with a keyboard | Ensure all elements are accessible using the Tab key | 1. Use the Tab key to navigate through the page | NA | All interactive elements should be accessible | All interactive elements should be accessible | Pass | It works properly
|  |  | TC_12 | User relies on a screen reader | Ensure screen readers can read all necessary content | 1. Enable screen reader (NVDA, JAWS) 2. Navigate through the page | Screen reader software | All important text should be read out correctly | All important text should be read out correctly | Pass | As expected
| Cross-Browser |  | TC_13 | User accesses the page on Chrome | Ensure all elements function correctly | 1. Open page in Chrome 2. Test key functions | Chrome browser | Page should work as expected | Page should work as expected | Pass | Work as expected
|  |  | TC_14 | User accesses the page on Firefox | Ensure all elements function correctly | 1. Open page in Firefox 2. Test key functions | Firefox browser | Page should work as expected | Page should work as expected | Pass | Work as expected
|  |  | TC_15 | User accesses the page on Edge | Ensure all elements function correctly | 1. Open page in Edge 2. Test key functions | Edge browser | Page should work as expected | Page should work as expected | Pass | Work as expected
| Error Handling |  | TC_16 | User has no referrals | Ensure system handles missing data gracefully | 1. Open Referrals page 2. Observe displayed message | No referrals | System should display "No referrals available" message | System should display "No referrals available" message | Pass | As expected
|  |  | TC_17 | User has no unclaimed earnings | Ensure system prevents invalid claims | 1. Click "Claim Earnings" when balance is $0 2. Observe system response | $0 earnings | System should disable the button or show an error message | System should disable the button or show an error message | Pass | As expected
|  |  | TC_18 | User enters an incorrect referral link | Ensure system handles invalid referral links properly | 1. Open a broken referral link 2. Observe system response | Invalid referral URL | System should display an error message | System should display an error message | Pass | As expected

## FAQs
TEST CASES for "FAQs"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-11 | Functional | Verify FAQs Page | TC_01 | User is on the FAQ page | Verify FAQ accordion expands on click | 1. Navigate to the FAQ section 2. Click on any question 3. Check if the answer expands | Question: What payments method do you accept? | The answer should expand showing relevant content | The answer should expand showing relevant content | Pass | it shows relevant content
|  |  | TC_02 | FAQ answer is expanded | Verify FAQ accordion collapses on second click | 1. Click on an expanded question 2. Check if the answer collapses | NA | The answer should collapse | The answer should collapse | Pass | As expected
|  |  | TC_03 | User is on the FAQ page | Verify only one FAQ answer is expanded at a time | 1. Open one FAQ 2. Open another FAQ 3. Check if the first FAQ collapses | NA | Previous FAQ should collapse when another FAQ is opened | Previous FAQ should collapse when another FAQ is opened | Pass | As expected
| Usability |  | TC_04 | User is on the FAQ page | The FAQ text should be clear and readable | 1. Observe the font size, style, and contrast | NA | Text should be readable without strain | Text should be readable without strain | Pass | font should be readable
| Performance |  | TC_05 | User is on the FAQ page | Verify FAQ section loads within an acceptable time | 1. Open the landing page 2. Check FAQ section loading time | NA | FAQ section should load within 2 seconds | FAQ section should load within 2 seconds | Pass | As expected
|  |  | TC_06 | Slow network simulated | Check if FAQs are usable under slow networks | 1. Simulate a 3G connection 2. Load the FAQ section | NA | FAQs should load without breaking UI | FAQs should load without breaking UI | Pass | Sometimes it breakes in very slow internet connection
| Accessibility |  | TC_07 | Screen reader is enabled | Verify screen reader compatibility | 1. Enable a screen reader 2. Navigate through FAQs | NA | Screen reader should announce the question and answer properly | Screen reader should announce the question and answer properly | Pass | As expected
|  |  | TC_08 | User is using a keyboard | FAQ questions should be accessible using the keyboard | 1. Use Tab key to navigate 2. Use Enter key to expand/collapse FAQ | NA | Keyboard navigation should work without issues | Keyboard navigation should not work | Fail | Not works
| Cross-Browser |  | TC_09 | User has different browsers installed | FAQs should work the same across browsers | 1. Open the FAQ section in Chrome, Firefox, Edge 2. Check for consistency | Browsers: Chrome, Firefox, Edge | The FAQ section should function correctly in all browsers | The FAQ section should function correctly in all browsers | Pass | it works in all browsers
| Cross-Device |  | TC_10 | User has different devices | The FAQ section should be usable on mobile, tablet, and desktop | 1. Open the FAQ section on mobile, tablet, and desktop 2. Check layout | Devices: Mobile, Tablet, Desktop | FAQs should be fully responsive on all devices | FAQs should be fully responsive on all devices | Pass | As expected
| Functional |  | TC_11 | Dark mode is enabled | FAQs should be readable and well-formatted in dark mode | 1. Enable dark mode 2. Observe FAQ section | Dark mode enabled | Text should be readable without layout issues | Text should be readable without layout issues | Pass | As expected
| Security |  | TC_12 | User is not logged in | Check if non-admins can alter FAQs | 1. Try to edit an FAQ without permissions | N/A | Editing should be restricted to authorized users only | Editing should be restricted to authorized users only | Pass | As expected

## Proxy Guide
TEST CASES for "Proxy Guide"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-12 | Functional | Verify API Settings Button | TC_01 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Verify API Settings Button | 1. Navigate to the API Guide section 2. Click on API Setting Button | NA | Redirects to API settings page | "API Setting" button is not functional | Fail | Make it functional
|  | Verify Install Extension Button | TC_02 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Verify Install Extension Button | 1. Navigate to the API Guide section 2. Click Install Extension on Chrome button | NA | Redirects to Chrome extension page | Redirects to Chrome extension page | Pass | As expected
|  | Verify YouTube Video Play | TC_03 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Verify YouTube Video Play | 1. Navigate to the API Guide section 2. Click play button on video | NA | Video starts playing | Video starts playing | Pass | As expected
| Usability | Check Navigation Functionality | TC_04 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Check Navigation Functionality | 1. Navigate to the API Guide section 2. Click Previous Page, Next Page buttons | NA | Navigates correctly | Navigates correctly | Pass | As expected
|  | Verify Sidebar Navigation | TC_05 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Verify Sidebar Navigation | 1. Navigate to the API Guide section 2. Click on each sidebar option | NA | Correct page loads for each option | Correct page loads for each option | Pass | As expected
| Performance | Check Page Load Time | TC_06 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Measure time to load page | 1. Navigate to the API Guide section 2. Load page and record time | NA | Page loads within acceptable time | Page loads within 2 sec acceptable time | Pass | As expected
|  | Verify Button Response Time | TC_07 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Measure time after clicking buttons | 1. Navigate to the API Guide section 2. Click buttons and record response time | NA | Buttons respond instantly | Buttons respond instantly | Pass | As expected
| Accessibility | Check Keyboard Navigation | TC_08 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Check Keyboard Navigation | 1. Navigate to the API Guide section 2. Use Tab key for navigation | Tab Button | All elements are reachable via keyboard | elements are not reachable via keyboard | Fail | Need to fix
|  | Verify Screen Reader Compatibility | TC_09 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Verify Screen Reader Compatibility | 1. Navigate to the API Guide section 2. Enable screen reader | NA | Screen reader reads all elements correctly | Screen reader reads all elements correctly | Pass | As expected
| Cross-Browser | Check Page Rendering in Chrome | TC_10 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Open page in Chrome browser | 1. Open Chrome 2. Navigate to the API Guide section | NA | Page loads correctly | Page loads correctly | Pass | As expected
|  | Check Page Rendering in Firefox | TC_11 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Open page in Firefox browser | Open in Firefox | NA | Page loads correctly | Page loads correctly | Pass | As expected
|  | Check Page Rendering in Edge | TC_13 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Open page in Edge browser | Open in Edge | NA | Page loads correctly | Page loads correctly | Pass | Loads correctly
| Usability | Verify API Guide Title Visibility | TC_14 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Ensure "API Guide" title is visible | 1. Navigate to the API Guide section 2. Check if title is displayed | NA | Title is clearly visible | Title is clearly visible | Pass | As expected
| Functional | Verify Sidebar Active State | TC_15 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Check if active menu item is highlighted | 1. Navigate to the API Guide section 2. Click on each sidebar item | NA | Active item is highlighted | Active item is highlighted | Pass | As expected
| Performance | Verify Video Load Time | TC_16 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Check if video loads without delay | 1. Navigate to the API Guide section 2. Click play on video | NA | Video starts playing within 2 seconds | Video starts playing within 2 seconds | Pass | As expected
| Functional | Verify YouTube Channel Redirection | TC_17 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Verify YouTube Channel Redirection | 1. Navigate to the API Guide section 2.Click on YouTube Channel button | NA | Redirects to YouTube channel | Redirects to YouTube channel | Pass | As expected
|  | Check API Settings Button on Mobile | TC_18 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Check API Settings Button on Mobile | 1. Navigate to the API Guide section 2. Click API Settings button on mobile | NA | Redirects to API settings page | Button is not functional | Fail | As expected
| Usability | Verify Responsive Design | TC_19 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Check layout on mobile | Open page on mobile device | NA | Layout adjusts correctly | Layout adjusts correctly | Pass | As expected
| Functional | Verify Chrome Extension Button on Mobile | TC_20 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Verify Chrome Extension Button on Mobile | 1. Navigate to the API Guide section 2. Click Install Extension on Chrome on mobile | NA | Should not be accessible or should redirect | Should not be accessible or should redirect | Pass | As expected
| Accessibility | Check Contrast Ratio | TC_21 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Check text and background contrast ratio | 1. Navigate to the API Guide section 2. Inspect using accessibility tools | NA | Meets accessibility standards | Meets accessibility standards | Pass | As expected
| Functional | Verify Tooltip Visibility | TC_22 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Hover over icons to check tooltips | 1. Navigate to the API Guide section 2. Hover over API Settings button | NA | Tooltips appear correctly | Tooltips appear correctly | Pass | As expected
|  | Verify Settings Icon Functionality | TC_23 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Click on settings icon | 1. Navigate to the API Guide section 2. Click settings icon | NA | Settings panel appears | Settings panel appears | Pass | As expected
| Usability | Verify Link Color Changes on Hover | TC_24 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Hover over sidebar links | 1. Navigate to the API Guide section 2. Hover over links | NA | Links change color on hover | Links change color on hover | Pass | As expected
| Performance | Check Page Load Time on Mobile | TC_25 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Measure time to load page | Open page on mobile | NA | Page loads within acceptable time | Page loads within acceptable time | Pass | As expected
| Functional | Verify Video Pause Functionality | TC_26 | User successfully registered and visited to Dashboard " https://app.lightningproxies.net/dashboard " | Pause the embedded YouTube video | 1. Navigate to the API Guide section 2. Click pause button on video | NA | Video pauses | Video pauses | Pass | As expected
|  | Verify Landing Page Load | TC_27 | NA | Verify Landing Page Load | Open website landing page | NA | Landing page loads successfully | Landing page loads successfully | Pass | As expected

## Join Discord Server & Telegram
TEST CASES for "Join Discord Server & Telegram channel"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-14 | Functional | Verify Join Discord Server & Telegram Channel | TC_01 | User is on the page Home Page | Verify the Discord link should open the correct URL | 1. Navigate to the page 2. Click on the "Join Discord Server" link 3. Verify the redirection | Expected Discord URL | The link should open the Discord invite page | The link should open the Discord invite page | Pass | As expected
|  |  | TC_02 | User is on the page Home Page | Verify the Telegram link should open the correct URL | 1. Navigate to the page 2. Click on the "Join Telegram Channel" link 3. Verify the redirection | Expected Telegram URL | The link should open the Telegram invite page | The link should open the Telegram invite page | Pass | As expected
|  |  | TC_03 | User is on the page Home Page | Verify links are not broken | 1. Inspect the href attribute of the links 2. Verify if they return a 404 error | NA | The links should not be broken and should lead to valid pages | The links should not be broken and should lead to valid pages | Pass | As expected
| Usability |  | TC_04 | User is on the page Home Page | Verify Discord and Telegram icons should be properly visible | 1. Observe the section layout 2. Verify if icons are clearly visible and aligned | NA | Icons should be properly aligned and visible | Icons should be properly aligned and visible | Pass | As expected
|  |  | TC_05 | User is on the page Home Page | Verify Hovering over links should provide feedback (e.g., color change) | 1. Hover over the "Join Discord Server" and "Join Telegram Channel" links 2. Observe changes | NA | Hovering should show a visual cue (color change) | Hovering should show a visual cue (color change) | Pass | As expected
| Performance |  | TC_06 | User is on the page Home Page | Ensure the section loads within an acceptable time frame | 1. Load the landing page 2. Measure the time taken for this section to appear | NA | Section should load within <2 seconds | Section should load within <2 seconds | Pass | As expected
|  |  | TC_07 | User is on the page Home Page | Measure the time taken for redirection | 1. Click on the links 2. Measure the redirection time | NA | Redirection should take less than <3 seconds | Redirection should take less than <3 seconds | Pass | As expected
| Accessibility |  | TC_08 | User is using a keyboard | Verify Section should be accessible using the keyboard | 1. Use the Tab key to navigate 2. Press Enter to open links | NA | Keyboard navigation should work properly | Keyboard navigation should work properly | Fail | need to fix keyboard navigation not works
| Cross-Browser |  | TC_09 | User has different browsers installed | Section should work the same across browsers | 1. Open the page in Chrome, Firefox, Edge 2. Check for consistency | Browsers: Chrome, Firefox, Edge | Section should display and function correctly in all browsers | Section should display and function correctly in all browsers | Pass | As expected
| Cross-Device |  | TC_10 | User has different devices | Verify Section should be usable on mobile, tablet, and desktop | 1. Open the page on mobile, tablet, and desktop 2. Check layout | Devices: Mobile, Tablet, Desktop | Section should be fully responsive on all devices | Section should be fully responsive on all devices | Pass | As expected
| Functional |  | TC_11 | User is on the Home page | Verify Clicking the links should open a new tab | 1. Click the links and observe if a new tab opens | N/A | Links should open in a new tab, not the same window | Links should open in a new tab, not the same window | Pass | works properly

## Profile
TEST CASES for "Profile"
Test Scenario ID | Test Type | Test Scenario | Test Case ID | Pre-Condition | Test Case Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Comments
TS-15 | Functional | Verify the Profile page | TC_01 | User must be logged in | Ensure correct user details (username, email, etc.) are displayed | 1. Navigate to Account Settings page 2. Verify displayed information | Username- shivendra, Email- shivendramasai2024@gmail.com Joined- Mar 25, 10:00 UTC | User details should match the database | details are matched but Joined date not matched | Fail | Joined date not matched
|  |  | TC_02 | User must be on the Account Settings page | Validate clicking "Update Information" saves updated details | 1. Modify details 2. Click "Update Information" | Username- shivendra, Email- shivendramasai2024@gmail.com | Changes should be successfully saved | Changes should be successfully saved | Pass | As expected
|  |  | TC_03 | User should know the current password | Validate that the password change is successful | 1. Enter current password 2. Enter new password 3. Confirm new password 4. Click "Reset Password" | Current Password- Singh@7607, New Password- Shivendra@9621 | Password should be changed successfully | Password should be changed successfully | Pass | Successfully changed
|  |  | TC_04 | User must scan the QR code | Verify 2FA activation using OTP | 1. Scan QR Code 2. Enter OTP 3. Click "Enable 2FA" | OTP: 448569 | 2FA should be enabled | 2FA should be enabled | Pass | As expected
|  |  | TC_05 | User must be on API Key section | Verify API Key change functionality | 1. Click "Change API Key" 2. Verify new key generation | Previous API Key vs New Key | API Key should change successfully | API Key should change successfully | Pass | As expected
| Usability |  | TC_06 | User must be on Account Settings page | Check input fields and buttons are correctly aligned | 1. Navigate to Account Settings page 2. Visually inspect layout | UI elements | All elements should be properly aligned | All elements should be properly aligned | Pass | As expected
|  |  | TC_07 | User must enter incorrect data | Validate error message when entering incorrect email format | 1. Enter invalid email 2. Click "Update Information" | Invalid Email: singhshivendra7607@gmail.c | Proper validation message should be displayed | Proper validation message should not be displayed | Fail | when write only .com it is not showing error message
| Performance |  | TC_08 | User must navigate to the page | Measure time taken for page load | 1. Navigate to Account Settings page 2. Use developer tools to measure load time | N/A | Page should load within 2-3 seconds | Page should load within 2-3 seconds | Pass | Loaded properly
| Accessibility |  | TC_09 | User must not use a mouse | Ensure all elements are accessible via the keyboard | 1. Use TAB key to navigate fields 2. Verify accessibility | Keyboard navigation | All fields should be reachable via keyboard | All fields should be reachable via keyboard | Pass | As expected
| Cross-Browser |  | TC_11 | Test on multiple browsers | Check page on Chrome, Firefox, Edge | 1. Open page in different browsers 2. Verify layout | Chrome, Firefox, Edge | Layout should be consistent across browsers | Layout should be consistent across browsers | Pass | As expected
| Functional |  | TC_14 | User must enter incorrect phone format | Ensure error message appears for incorrect phone number | 1. Enter invalid phone number 2. Click "Update Information" | Phone- +919621318299 | Error message should appear | Error message should appear | Pass | Error messsage appeared
|  |  | TC_15 | User must enter incomplete data | Ensure form does not submit when mandatory fields are blank | 1. Leave mandatory fields blank 2. Click "Update Information" | Blank fields | Proper validation message should be displayed | Proper validation message should be displayed | Pass | As expected
| Functional |  | TC_16 | User must be logged in | Ensure session expires after a set time of inactivity | 1. Log in 2. Stay inactive for a period 3. Try updating details | 2 h | User should be logged out after timeout | User should not be logged out after timeout | Fail | should not be logged out after timeout
|  |  | TC_17 | User must have billing details | Ensure updates to billing information are saved correctly | 1. Edit billing details 2. Click "Update Information" | New Billing Email, Address | Billing details should be updated successfully | Billing details should be updated successfully | Pass | As expected
| Usability |  | TC_18 | User must be on Account Settings page | Ensure tooltips/help text are available for key fields | 1. Hover over fields 2. Check for tooltip/help text | N/A | Relevant help text should appear | Relevant help text should appear | Pass | As expected
| Performance |  | TC_19 | User must submit a form | Ensure form submits within an acceptable time limit | 1. Fill form 2. Click "Update Information" 3. Measure time taken | Form data | Submission should be processed within 2-3 seconds | Submission is not functional | Fail | Submission is not functional and not showing Successfully update message
| Accessibility |  | TC_20 | User must view the page | Ensure sufficient contrast between text and background | 1. Open page 2. Check readability | Page colors | Text should be clearly visible | Text should be clearly visible | Pass | As expected
| Cross-Browser |  | TC_21 | Test on multiple browsers | Ensure all buttons work across browsers | 1. Open page in different browsers 2. Click all buttons | Chrome, Firefox, Edge | Buttons should function correctly in all browsers | Buttons should function correctly in all browsers | Pass | As expected